## Sheet1
Assumptions: |  |  |  | Questions:
Payment Data file - what the user actually paid
Transaction file - what the user is expected to pay |  |  |  | Does the Transaction Service Data file contain a date showing that these are the transactions for x date?
Payment Data file will be dropped into a queue location |  |  |  | Should the Lender name be editable? - requirements are vague
Under Requirement 1, the "Create an exception….." statement is for creating a test case.
Queues: use status field to denote queue
Requirement | Details | Steps | Initial Est.
Business Requirement 1 | Import todays data file of payment data into the transaction system (Background Process) | User upload's (imports) payment data file from network location. Create upload screen (UI). | 0.5
|  | When uploaded, read and parse the file. | 0.1
|  | Insert parsed payment data into transaction system database. | 0.2
Business Requirement 2 | Check for missing transaction amount in todays file –blank or mismatch (background process) | Reconciliation process: - Compare daily payment date file amounts to transaction file amounts; check for blank or missing; check for mismatched payment amounts; mark the record with an error flag; and add mismatched records to a mis-matched table with a status field to show the reason. | 0.5
Business Requirement 3 | User selects today's date and reconciles. | Trigger reconciliation process - see BR#2 | 0.5 | This requirement is half a week
Screen option for reconcile process. (Date selection filter)
Display status of reconciliation - pass or fail
Business Requirement 4 | Display status of reconciliation - in balance or adjust user queue | User prompt to make updates or quit | 0.5 | This requirement is half a week
Option to update/correct a payment records: - if yes BR#5; if no user notified file's out of balance and quit
Business Requirement 5 | Allow user to update payment information in a single payment transaction | Display the payment records that have exceptions. (mis-matched table) | 0.2
|  | User can select a record to edit. And then display the payment data record and transaction data record | 0.5
|  | Dropdown list to allow lender name change. (see questions) | 0.1
|  | Update transaction amount | 0.1
|  | Update reason code from provided list. | 0.1
|  | User asked if they would like to confirm the update and send for supervisor approval. | 0.1
|  | When the update is confirmed, the username and date are added to the updated transaction (update user and date) and the status is changed to "Awaiting Approval" for supervisor to review.. | 0.1
Business Requirement 6 | Create summary of the changed payment transaction detail and put in a queue for supervisor approval | Create supervisor review screen (queue).
Displays the updated payment records that need to be approved. Displays data from original payment data file, the transaction data file, and the updated mis-matched table